## Test Summary
SpaceXP HRIS - Admin Portal
Admin Module Test Summary
Tested By: V. Deshanth
Browser: Mozilla Firefox, Microsoft Edge
OS: Windows 11
Application URL: |  | https://hris.softwareplus.lk/login
Test Case Summary
Total | 127
Pass | 81
Fail | 46
Pass Percentage | 63.8%
Fail Percentage | 36.2%
Bug Summary
Total | 49
Critical | 7
High | 20
Medium | 22
Low | 0
Key Findings
Session termination during critical payroll actions (create/edit contract, generate all payslips) |  |  | Critical
Onboarding pipeline breaks at 4th stage, marks employee completed prematurely
Leave request page goes blank on create
Individual payslip creation fails with database argument error
"Silent failure" pattern across modules: error shown but action succeeds after refresh (Add Employee, Document Request, Rotating Shift/Work Type Assign) |  |  | High
Performance module editing functions fail with 500 error (Objectives, Key Results)
Leave management failures: assign leave fails, delete fails, "No leave allocation found" error
Payroll download icon opens view instead of downloading
Bonus points saved but not visible in list
Performance period creation fails
Biometric device addition fails with 400 error
Responsiveness completely broken on mobile/tablet
Login page loads slow in Firefox (>4 seconds)
3-dot menus unclickable on rightmost cards (Open Jobs, Leave Types, Allowances) |  |  | Medium
View All Notifications button non-responsive
Personal Dashboard link does not open
Sidebar collapses unexpectedly (Offboarding) or indicator shifts incorrectly
Edit buttons non-responsive (Leave Types, Assigned Leave)
View Details button non-responsive (Open Jobs)
Group By functionality not working (Attendance Requests)
Search field allows only one character at a time (Deductions)
UI issues: Payslip header broken, allowance color ignored, interviewers card text unreadable
Employee selection window lacks confirmation button
Filter shows all employees instead of filtered results

## Test Scenario
SpaceXP HRIS - Admin Portal
Test Scenario Document
Tested By: V. Deshanth
Application URL | https://hris.softwareplus.lk/login
Browser | Mozilla Firefox, Microsoft Edge
Operating system | Windows 11
Test Scenario ID | Module | Test Scenario
TS_01 | Login page | Verify login page loads sucessfully
TS_02 | Authentication | Verify admin login functionality
TS_03 | Authentication | Verify admin signup functionality
TS_04 | Fogot password | Verify forgot password
TS_05 | Create account | Verify "Contact HR Admin" functionality
TS_06 | Dashboard | Verify sidebar toggle functionality
TS_07 | Dashboard | Verify admin dashboard loads without errors
TS_08 | Authentication | Verify logout functionality
TS_09 | Settings | Verify update feature on company profile section
TS_10 | Settings | Verify update on User Roles & Permissions section
TS_11 | Settings | Verify update on Security section
TS_12 | Dashboard | Verify export report feature
TS_13 | Dashboard | Verify payroll execution
TS_14 | Navigation | Verify app navigation functionality
TS_15 | Recruitment | Verify recruitment management functionality
TS_16 | Leave requests | Verify creating a new leave request
TS_17 | Reimbursements | Verify reimbursements management functionality
TS_18 | Asset management | Verify assigning new assets
TS_19 | Help desk | Verify ticket management functionality
TS_20 | AI HR assistance | Verify assistance functionality
TS_21 | Recruitment Survey | Verify adding new survey
TS_22 | Recruitment Survey | Verify survey template management
TS_23 | Recruitment Survey | Verify survey duplication
TS_24 | Recruitment Survey | Verify survey deletion
TS_25 | Candidates | Verify create new candidate functionality
TS_26 | Candidates | Verify scheduling an interview
TS_27 | Candidates | Verify deleting a candidates record
TS_28 | Candidates | Verify bulk status update
TS_29 | Candidates | Verify candidate details export functionality
TS_30 | Interview | Verify scheduling an interview
TS_31 | Recruitment view | Verify hiring report export functionality
TS_32 | Open Jobs | Verify jobs management functionality
TS_33 | Recruitment | Verify recruitment stage management functionality
TS_34 | Skill zone | Verify candidate view funcionality based on skills
TS_35 | Onboarding | Verify add new employee to onboarding functionality
TS_36 | Onboarding | Verify pipeline procedure
TS_37 | Employee | Verify employee management functionality
TS_38 | Document request | Verify create new document request functionality
TS_39 | Shift request | Verify shift request management functionality
TS_40 | Work type request | Verify work type request management functionality
TS_41 | Rotating shift assign | Verify rotating shift assign functionality
TS_42 | Rotating shift assign | Verify rotating shift view functionality
TS_43 | Rotating work type assign | Verify action functionality
TS_44 | Rotating work type assign | Verify rotating work type management functionality
TS_45 | Disciplinary actions | Verify take an action functionality
TS_46 | Disciplinary actions | Verify deletion of employee disciplinary actions
TS_47 | Policies | Verify policy management functionality
TS_48 | Organization chart | Verify viewing of organizational chart
TS_49 | My other requests | Verify other requests management functionality
TS_50 | Attendance | Verify attendance dashboard view functionality
TS_51 | Biometric devices | Verify biometric device management functionality
TS_52 | Attendances | Verify attendance management functionality
TS_53 | Attendances | Verify attendance validation functionality
TS_54 | Attendance requests | Verify attendance request management functionality
TS_55 | Hour count | Verify hour count management functionality
TS_56 | Work records | Verify view, search and filter work records functionality
TS_57 | Attendance activities | Verify attendance records management functionality
TS_58 | Late come early out | Verify late come/early out records management functionality
TS_59 | Leave dashboard | Verify leave request management funtionality
TS_60 | Leave | Verify leave assignment functionality
TS_61 | Payroll contract | Verify payroll contract management functionality
TS_62 | Allowances | Verify allowances management functionality
TS_63 | Deductions | Verify deductions management functionality
TS_64 | Payslips | Verify payslip management functionality
TS_65 | Loans | Verify loan management functionality
TS_66 | Federal Tax | Verify federal tax management functionality
TS_67 | Payroll requests | Verify payrol request functionalities
TS_68 | Performance objective | Verify performance objective management functionalities
TS_69 | Performance feedback | Verify performance feedback management functionalities
TS_70 | Performance meetings | Verify performance meeting management functionalities
TS_71 | Employee bonus point | Verify employee bonus point management
TS_72 | Performance period | Verify creating performance period
TS_73 | Question template | Verify creating question templates
TS_74 | Offboarding | Verify exit process management of employees
TS_75 | Project | Verify create new project functionality
TS_76 | Configuration | Verify system configuration management functionalities

## Test Case Document
SpaceXP HRIS - Admin Portal
Test Case Document
Tested by: V. Dehanth
Application URL |  | https://hris.softwareplus.lk/login
Browser |  | Mozilla Firefox, Microsoft Edge
Operating System |  | Windows 11
TC ID | Test Scenario | Test Title | Pre - Conditions | Test Steps | Link | Test Data | Expected Result | Actual Result | Status | Bug ID
TC_01 | Verify Login page loads sucessfully | Verify login page loads successfully within 4 seconds | User has a working internet connection and have firefox and edge browsers open | 1. Open browser and enter the URL and open DevTools(F12) 2. Navigate to network tab 3. Reload the page 4. Wait for the page to load fully and record the time | https://hris.softwareplus.lk/login | No data required to enter | Login page should load successfully within 4 seconds across browsers | Page load time in Edge: less than 2 seconds Page load time in Firefox: More than 4 seconds | Fail | Bug_01
TC_02 | Verify admin login functionality | Verify admin user can login successfully with valid credentials | Admin user account should exist | Open URL→ Enter valid email→Enter valid password→ Click sign in to dashboard | https://hris.softwareplus.lk/login | Email: admin@spacexp.com Password: admin123 | User should be logged in and redirected to dashboard | User is successfully logged in and redirected to dashboard | Pass
TC_03 | Verify admin login | Verify error message is displayed for invalid admin login credentials | Admin user account should exist | Open URL→ Enter invalid email/password→ Click sign in to dashboard | https://hris.softwareplus.lk/login | Email: wrong@email.com Password: wrong123 | Error message should be displayed | Error message is displayed as invalid email or password | Pass
TC_04 | Verify admin login | Verify validation message is displayed when login fields are empty | Login page should be open | Open URL→ Leave both email and password fields empty→ Click sign in to dashboard | https://hris.softwareplus.lk/login | No data required to enter | Error message should be displayed | Error message is displayed as 'Please fill in all fields' | Pass
TC_05 | Verify admin login | Verify Forgot Password link redirects user to password reset page | Login page should be open | 1. Click 'forgot password' | https://hris.softwareplus.lk/login | No data required to enter | Application should redirect to password reset page | Clicking 'Forgot password' does not redirect to password reset page | Fail | Bug_02
TC_06 | Verify 'Contact HR Admin' functionality | Verify Contact HR Administrator link redirects correctly | Login page should be open | 1. Click 'Contact HR Administrator' | https://hris.softwareplus.lk/login | No data required to enter | User should be redirected to a page where they can contact HR regarding account creation | No changes happen upon clicking the link | Fail | Bug_03
TC_07 | Verify sidebar toggle functionality | Verify sidebar toggle button expands and collapses sidebar correctly | User should be logged in and be on the dashboard | 1. Login to the application 2. Click on the sidebar toggle button on the top left corner next to the logo 3. Observe the change | https://hris.softwareplus.lk/dashboard | No data required to enter | The sidebar should open and close when the sidebar button is clicked | When the button is clicked, only the direction of the button changes but the sidebar remains open | Fail | Bug_04
TC_08 | Verify admin dashboard loads without errors | Verify admin dashboard loads correctly without UI rendering issues | User should have an account and be on the login page | 1. Login to the application 2. Check how the dashboard is loaded | https://hris.softwareplus.lk/dashboard | No data required to enter | Admin dashboard should load successfully without any errors | The user is logged into the dashboard successfully, but the dashboard shows a dark or dim effect on the entire interface | Fail | Bug_05
TC_09 | Verify logout functionality | Verify user can logout successfully from the system | User should be logged into the system | 1. Login to the application 2. Click on the admin user dropdown button on the top right corner 3. Click logout | https://hris.softwareplus.lk/dashboard | No data required to enter | User should be logged out of the system and redirected to the login page | User is successfully logged out and redirected to the login page | Pass
TC_10 | Recruitment | Verify new candidate can be created successfully | User should be logged into the system and be on the candidates page | Recruitment → Candidates → Create → Fill form → Click Create Candidate | https://hris.softwareplus.lk/recruitment/candidates | Enter valid data | Candidate should be created successfully | Candidate successfully created | Pass
TC_11 | Recruitment | Verify candidate details can be edited successfully | User should be logged into the system and be on the candidates page | Recruitment → 3 dots menu on a candidate card → Edit → Update fields → Click Save Changes | https://hris.softwareplus.lk/recruitment/candidates | Enter valid data | Candidate details should update successfully | Candidate successfully updated | Pass
TC_12 | Recruitment | Verify candidate can be deleted successfully | User should be logged into the system and be on the candidates page | Recruitment → 3 dots menu on a candidate card → Delete → Confirm | https://hris.softwareplus.lk/recruitment/candidates | No data required to enter | Candidate should be deleted | Candidate successfully deleted | Pass
TC_13 | Recruitment | Verify bulk status update works for selected candidates | User should be logged into the system and be on the candidates page | Recruitment → Select Candidates → Actions → Bulk Status Update | https://hris.softwareplus.lk/recruitment/candidates | Enter valid data | Status of selected candidates should update | Status updated successfully | Pass
TC_14 | Recruitment | Verify interview can be scheduled successfully | Candidates should be added to the recruitment pipeline | Recruitment → Interview → Schedule Interview → Select Candidate → Fill form → Click Schedule | https://hris.softwareplus.lk/recruitment/interview | Enter valid data | Interview should be scheduled | Interview scheduled successfully | Pass
TC_15 | Recruitment | Verify interview can be rescheduled successfully | Interview should be scheduled and displayed in the page | Recruitment → Interview → Select Candidate → Reschedule | https://hris.softwareplus.lk/recruitment/interview | Enter valid data | Interview should be rescheduled | Interview rescheduled successfully | Pass
TC_16 | Recruitment | Verify hiring report can be exported successfully | User should be on the recruitment view page | Recruitment → Recruitment View → Hiring Report | https://hris.softwareplus.lk/recruitment/view | No data required to enter | Hiring report should download | Hiring report downloaded | Pass
TC_17 | Recruitment | Verify Active Jobs card redirects to Open Jobs page | User should be on the recruitment view page | Recruitment → Recruitment View → Active Jobs | https://hris.softwareplus.lk/recruitment/view | No data required to enter | Should open Open Jobs page | Opens Open Jobs page | Pass
TC_18 | Recruitment | Verify New Candidates card redirects to Candidates page | User should be on the recruitment view page | Recruitment → Recruitment View → New Candidates | https://hris.softwareplus.lk/recruitment/view | No data required to enter | Should open Candidates page | Opens Candidates page | Pass
TC_19 | Recruitment | Verify Top Interviewers card text is clearly visible against background | User should be on the recruitment view page | Recruitment → Recruitment View → Observe Top Interviewers card | https://hris.softwareplus.lk/recruitment/view | No data required to enter | Text should be readable against background | Black text not readable on dark navy blue background and text does not fit within the card. | Fail | Bug_06
TC_20 | Recruitment | Verify new job can be posted successfully | User should be on the open jobs page | Recruitment → Open Jobs → Post New Job → Fill form → Click Post Job | https://hris.softwareplus.lk/recruitment/open-jobs | Enter valid data | Job should post successfully | Job posted successfully | Pass
TC_21 | Recruitment | Verify View Details option opens job details successfully | User should be on the open jobs page | Recruitment → Open Jobs → 3-dots menu → View Details | https://hris.softwareplus.lk/recruitment/open-jobs | No data required to enter | Job details should open | No response from button click | Fail | Bug_08
TC_22 | Recruitment | Verify job posting can be closed successfully | User should be on the open jobs page | Recruitment → Open Jobs → 3-dots menu → Close Job Posting | https://hris.softwareplus.lk/recruitment/open-jobs | No data required to enter | Job should be closed | Job closed successfully | Pass
TC_23 | Recruitment | Verify 3-dots menu is fully clickable on all job cards | User should be on the open jobs page | Recruitment → Open Jobs → Resize browser → Click 3-dots on rightmost card | https://hris.softwareplus.lk/recruitment/open-jobs | No data required to enter | Menu should open | Menu not clickable at right edge | Fail | Bug_09
TC_24 | Recruitment | Verify View Applicants redirects to Candidates page | User should be on the open jobs page | Recruitment → Open Jobs → View Applicants | https://hris.softwareplus.lk/recruitment/open-jobs | No data required to enter | Should open Candidates page | Opens Candidates page | Pass
TC_25 | Recruitment | Verify new recruitment stage can be added successfully | User should be on the stages page | Recruitment → Stages → Add New Stage → Fill form → Click Create | https://hris.softwareplus.lk/recruitment/stages | Enter valid data | Stage should be added | Stage added successfully | Pass
TC_26 | Recruitment | Verify recruitment stage can be edited successfully | User should be on the stages page | Recruitment → Stages → Edit Stage → Update → Click Update | https://hris.softwareplus.lk/recruitment/stages | Enter valid data | Stage should update | Stage updated successfully | Pass
TC_27 | Recruitment | Verify skill distribution data is displayed correctly | User should be on the Skill Zone page | Recruitment → Skill Zone → Observe skill cards | https://hris.softwareplus.lk/recruitment/skill-zone | No data required to enter | Skills should display | Skills displayed | Pass
TC_28 | Recruitment | Verify View Candidates button redirects to Candidates interface | User should be on the Skill Zone page | Recruitment → Skill Zone → Click View Candidates | https://hris.softwareplus.lk/recruitment/skill-zone | No data required to enter | Should redirect to Candidates interface | Redirects correctly | Pass
TC_29 | Recruitment | Verify employee can be added to onboarding pipeline successfully | User should be on the Onboarding page | Recruitment → Onboarding → Add Employee → Select employee → Add to pipeline | https://hris.softwareplus.lk/onboarding | Select employee from the list | Employee should be added to pipeline | Employee added successfully | Pass
TC_30 | Recruitment | Verify onboarding pipeline stages update correctly | User should be added to the pipeline before updating the stages | Recruitment → Onboarding → Add employee → Click Mark Ready at each stage | https://hris.softwareplus.lk/onboarding | No data required to enter | Employee should progress through all stages | Progresses until 4th stage, then incorrectly marked as completed and pipeline disappears | Fail | Bug_10
TC_31 | Employee | Verify employee profile details can be updated successfully | User should be on the Employee profile page | Employee → Profile → Click Edit Profile → Fill details → Click Update | https://hris.softwareplus.lk/employee/employee-profile/ | Enter valid data | Profile should update successfully | Profile updated successfully | Pass
TC_32 | Employee | Verify new employee can be added successfully | User should be on the Employees page | Employee → Employees → Add Employee → Fill form → Click Add | https://hris.softwareplus.lk/employee-employees | Enter valid data | Employee should be added instantly | Shows “Internal server error”, but employee appears after refresh | Fail | Bug_20
TC_33 | Employee | Verify document request can be created successfully | User should be on the document requests page | Employee → Document Request → Create → Fill form → Save | https://hris.softwareplus.lk/employee-document-requests | Enter valid data | Request should appear instantly | Shows “Failed to create document request”, appears only after refresh | Fail | Bug_21
TC_34 | Employee | Verify document request can be deleted successfully | User should be on the document requests page | Employee → Document Request → Scroll list → Click Trash Bin | https://hris.softwareplus.lk/employee-document-requests | No data required to enter | Request should be deleted instantly | Request deleted instantly | Pass
TC_35 | Employee | Verify shift request can be created successfully | User should be on the shift requests page | Employee → Shift Request → Create → Fill form → Save | https://hris.softwareplus.lk/employee-shift-requests | Enter valid data | Request should appear instantly | Request created successfully | Pass
TC_36 | Employee | Verify shift request can be deleted successfully | User should be on the shift requests page | Employee → Shift Request → Click Trash Bin | https://hris.softwareplus.lk/employee-shift-requests | No data required to enter | Request should be deleted instantly | Request deleted instantly | Pass
TC_37 | Employee | Verify work type request can be created successfully | User should be on the work type requests page | Employee → Work Type Request → Create → Fill form → Save | https://hris.softwareplus.lk/employee-work-type-requests | Enter valid data | Request should appear instantly | Request created successfully | Pass
TC_38 | Employee | Verify work type request can be deleted successfully | User should be on the work type requests page | Employee → Work Type Request → Click Trash Bin | https://hris.softwareplus.lk/employee-work-type-requests | No data required to enter | Request should be deleted instantly | Request deleted instantly | Pass
TC_39 | Employee | Verify rotating shift assignment can be created successfully | User should be on the rotating shift assign page | Employee → Rotating Shift Assign → Assign → Fill form → Click Assign | https://hris.softwareplus.lk/employee-rotating-shift-assign | Enter valid data | Assignment should be created and appear instantly | Shows “Failed to assign rotating shift”, appears only after refresh | Fail | Bug_22
TC_40 | Employee | Verify rotating shift assignment can be deleted successfully | User should be on the rotating shift assign page | Employee → Rotating Shift Assign → Click Trash Bin | https://hris.softwareplus.lk/employee-rotating-shift-assign | No data required to enter | Assignment should be deleted instantly | Assignment deleted instantly | Pass
TC_41 | Employee | Verify rotating work type assignment can be created successfully | User should be on the rotating work type assign page | Employee → Rotating Work Type Assign → Assign → Fill form → Click Assign | https://hris.softwareplus.lk/employee-rotating-work-type-assign | Enter valid data | Assignment should appear instantly | Shows “Failed to assign work type”, appears only after refresh | Fail | Bug_23
TC_42 | Employee | Verify rotating work type assignment can be deleted successfully | User should be on the rotating work type assign page | Employee → Rotating Work Type Assign → Click Trash Bin | https://hris.softwareplus.lk/employee-rotating-work-type-assign | No data required to enter | Assignment should be deleted instantly | Assignment deleted instantly | Pass
TC_43 | Employee | Verify disciplinary action can be recorded successfully | User should be on the disciplinary actions page | Employee → Disciplinary Actions → Take Action → Fill form → Save | https://hris.softwareplus.lk/employee-disciplinary-actions | Enter valid data | Action should appear instantly | Action recorded successfully | Pass
TC_44 | Employee | Verify disciplinary attachment can be downloaded successfully | User should be on the disciplinary actions page | Employee → Disciplinary Actions → Create with attachment → Click Download | https://hris.softwareplus.lk/employee-disciplinary-actions | No data required to enter | Attachment should download | Logs user out, redirects to login page | Fail | Bug_24
TC_45 | Employee | Verify policy can be created successfully | User should be on the policies page | Employee → Policies → Create → Fill form → Publish | https://hris.softwareplus.lk/employee-policies | Enter valid data | Policy should appear instantly | Policy created successfully | Pass
TC_46 | Employee | Verify policy can be deleted successfully | User should be on the policies page | Employee → Policies → Click Trash Bin | https://hris.softwareplus.lk/employee-policies | No data required to enter | Policy should be deleted instantly | Policy deleted successfully | Pass
TC_47 | Employee | Verify organizational chart displays and filters correctly | User should be on the Organization chart page | Employee → Organizational Chart → View → Search names/departments | https://hris.softwareplus.lk/employee-organization-chart | No data required to enter | Chart should display and filter correctly | Chart displays and filters correctly | Pass
TC_48 | Employee | Verify other request can be created successfully | User should be on the My other requests page | Employee → My Other Requests → Create → Fill form → Submit | https://hris.softwareplus.lk/employee-other-requests | Enter valid data | Request should appear instantly | Request created successfully | Pass
TC_49 | Employee | Verify other requests can be searched successfully | User should be on the My other requests page | Employee → My Other Requests → Search bar | https://hris.softwareplus.lk/employee-other-requests | Enter valid data to search | Results should filter correctly | Results displayed correctly | Pass
TC_50 | Employee | Verify action buttons function correctly for all request statuses | User should be on the My other requests page | Employee → My Other Requests → Click Edit/Delete from actions column | https://hris.softwareplus.lk/employee-other-requests | No data required to enter | Buttons should work for all requests | Works only for pending requests, no proper indication for others as action buttons on non pending requests are not dimmed | Fail | Bug_25
TC_51 | Employee | Verify request status updates correctly after approval or rejection | User should be on the My other requests page | Employee → My Other Requests → Click Approve/Reject on pending requests | https://hris.softwareplus.lk/employee-other-requests | No data required to enter | Status should update instantly | Status updated successfully | Pass
TC_52 | Leave | Verify Personal Dashboard opens successfully from Leave Dashboard | User should be on the Leave dashboard page | Leave → Dashboard → Click Personal Dashboard card | https://hris.softwareplus.lk/leave-dashboard | No data required to enter | Personal dashboard should open | No response, dashboard not opening | Fail | Bug_26
TC_53 | Leave | Verify Leave Dashboard displays leave details correctly | User should be on the Leave dashboard page | Leave → Dashboard | https://hris.softwareplus.lk/leave-dashboard | No data required to enter | Leave details should display | Leave details displayed correctly | Pass
TC_54 | Leave | Verify admin can create My Leave Request successfully | User should be on the My Leave Reaquests page | Leave → My Leave Requests → Create → Fill form → Save | https://hris.softwareplus.lk/leave-my-requests | Enter valid data | Request should be created instantly | Error: “No leave allocation found” | Fail | Bug_27
TC_55 | Leave | Verify leave request can be created successfully | User should be on the Leave Requests page | Leave → Leave Request → Create → Fill form → Save | https://hris.softwareplus.lk/leave-requests | Enter valid data | Request should be created instantly | Page goes blank after clicking Save | Fail | Bug_28
TC_56 | Leave | Verify leave request can be deleted successfully | User should be on the Leave Requests page | Leave → Leave Request → Actions → Delete | https://hris.softwareplus.lk/leave-requests | No data required to enter | Request should be deleted instantly | Error: “Failed to delete” | Fail | Bug_29
TC_57 | Leave | Verify leave type can be created successfully | User should be on the Leave types page | Leave → Leave Types → Create → Fill form → Save | https://hris.softwareplus.lk/leave-types | Enter valid data | Leave type should be created instantly | Leave type created successfully | Pass
TC_58 | Leave | Verify leave can be assigned to selected employees successfully | User should be on the Leave types page | Leave → Leave Types → 3-dots menu → Assign Leave → Select employees → Apply | https://hris.softwareplus.lk/leave-types | Select employee from the list | Leave should be assigned to employees | Success message shown, but leave not visible in the assigned leave page | Fail | Bug_30
TC_59 | Leave | Verify leave type can be edited successfully | User should be on the Leave types page | Leave → Leave Types → 3-dots menu → Edit | https://hris.softwareplus.lk/leave-types | No data was entered | Leave type should be editable | No response from Edit button | Fail | Bug_31
TC_60 | Leave | Verify leave type can be deleted successfully | User should be on the Leave types page | Leave → Leave Types → 3-dots menu → Delete | https://hris.softwareplus.lk/leave-types | No data required to enter | Leave type should be deleted instantly | Error: “Failed to delete leave type” | Pass
TC_61 | Leave | Verify 3-dots menu is clickable on all leave type cards | User should be on the Leave types page | Leave → Leave Types → 3-dots menu on rightmost card | https://hris.softwareplus.lk/leave-types | No data required to enter | Menu should open | Menu not clickable on rightmost cards | Fail | Bug_32
TC_62 | Leave | Verify assigning Leave (Assigned Leave Page) | User should be on the Assigned Leave page | Leave → Assigned Leave → Assign → Fill form → Save | https://hris.softwareplus.lk/leave-assigned | Enter valid data | Leave should be assigned instantly | Error: “Failed to assign leaves” | Fail | Bug_33
TC_63 | Leave | Verify assigned leave can be edited successfully | User should be on the Assigned Leave page | Leave → Assigned Leave → Actions → Edit | https://hris.softwareplus.lk/leave-assigned | Enter valid data | Assigned leave should be editable | No response from Edit button | Fail | Bug_34
TC_64 | Leave | Verify assigned leave can be deleted successfully | User should be on the Assigned Leave page | Leave → Assigned Leave → Actions → Delete | https://hris.softwareplus.lk/leave-assigned | No data required to enter | Assigned leave should be deleted instantly | Assigned leave deleted successfully | Pass
TC_65 | Leave | Verify leave allocation request can be created successfully | User should be on the Leave Allocation Request page | Leave → Leave Allocation Request → Fill form → Save | https://hris.softwareplus.lk/leave-allocation-request | Enter valid data | Request should be created instantly | Request created successfully | Pass
TC_66 | Leave | Verify leave allocation request can be deleted successfully | User should be on the Leave Allocation Request page | Leave → Leave Allocation Request → Actions → Delete | https://hris.softwareplus.lk/leave-allocation-request | No data required to enter | Request should be deleted instantly | Request deleted successfully | Pass
TC_67 | Leave | Verify leave allocation request status updates correctly after approval or rejection | User should be on the Leave Allocation Request page | Leave → Leave Allocation Request → Actions → Approve/Reject | https://hris.softwareplus.lk/leave-allocation-request | No data required to enter | Request should update status instantly | Request approved/rejected successfully | Pass
TC_68 | Attendance | Verify biometric device can be added successfully | User should be on the Biometric Device Management page | Attendance → Biometric Devices → Add → Fill form → Click Add | https://hris.softwareplus.lk/attendance-biometric | Enter valid data | Device should be added instantly | Shows “Request failed with status code 400” | Fail | Bug_11
TC_69 | Attendance | Verify attendance record can be added successfully | User should be on the Attendances page | Attendance → Attendances → Fill form → Save | https://hris.softwareplus.lk/attendance-attendances | Enter valid data | Attendance should be added instantly | Attendance added successfully | Pass
TC_70 | Attendance | Verify attendance record can be deleted successfully | User should be on the Attendances page | Attendance → Attendances → Select employee → Actions → Delete | https://hris.softwareplus.lk/attendance-attendances | No data required to enter | Attendance should be deleted instantly | Attendance deleted successfully | Pass
TC_71 | Attendance | Verify attendance request can be created successfully | User should be on the Attendance Request page | Attendance → Attendances → Create → Fill form → Save | https://hris.softwareplus.lk/attendance-requests | Enter valid data | Request should appear instantly | Request created successfully | Pass
TC_72 | Attendance | Verify Hour Count redirects to Attendances page successfully | User should be on the Hour Account page | Attendance → Hour Count → Create → Redirect | https://hris.softwareplus.lk/attendance-hour-account | No data required to enter | Should redirect to Attendances page | Redirects correctly | Pass
TC_73 | Attendance | Verify work records can be searched successfully | User should be on the Work Records page | Attendance → Work Records → Search employee | https://hris.softwareplus.lk/attendance-work-records | Enter employee name | Records should display correctly | Records displayed correctly | Pass
TC_74 | Attendance | Verify work records can be exported successfully | User should be on the Work Records page | Attendance → Work Records → Export CSV | https://hris.softwareplus.lk/attendance-work-records | No data required to enter | Records should download | Records downloaded | Pass
TC_75 | Attendance | Verify attendance activities can be exported successfully | User should be on the Attendance Activites page | Attendance → Attendance Activities → Select employees → Export | https://hris.softwareplus.lk/attendance-activities | No data required to enter | Files should download | Files downloaded | Pass
TC_76 | Attendance | Verify late/early attendance data can be exported successfully | User should be on the Late come Early out pagge | Attendance → Late Come/Early Out → Select employees → Export | https://hris.softwareplus.lk/attendance-late-early | No data required to enter | Files should download | Files downloaded | Pass
TC_77 | Attendance | Verify My Attendance records can be searched and filtered successfully | User should be on the My attendances page | Attendance → My Attendance → Apply filter → Search | https://hris.softwareplus.lk/attendance-my-attendances | Enter employee name to search | Filtered/searched data should display | Data displayed correctly | Pass
TC_78 | Attendance | Verify My Attendance Request can be created successfully | User should be on the My Attendance Request page | Attendance → My Attendance Request → Create → Submit | https://hris.softwareplus.lk/attendance-my-requests | Enter valid data | Request should appear instantly | Request created successfully | Pass
TC_79 | Attendance | Verify attendance requests can be grouped by category successfully | User should be on the My Attendance Request page | Attendance → My Attendance Request → Group By | https://hris.softwareplus.lk/attendance-my-requests | No data required to enter | Requests should group by category | Button not working | Fail | Bug_12
TC_80 | Attendance | Verify attendance request status updates correctly after approval or rejection | User should be on the My Attendance Request page | Attendance → My Attendance Request → Approve/Reject | https://hris.softwareplus.lk/attendance-my-requests | No data required to enter | Status should update instantly | Status updated correctly | Pass
TC_81 | Attendance | Verify attendance request action buttons function correctly | User should be on the My Attendance Request page | Attendance → My Attendance Request → Edit/Delete | https://hris.softwareplus.lk/attendance-my-requests | No data required to enter | Buttons should work consistently | Works only for pending requests; delete button misleading | Fail | Bug_13
TC_82 | Performance | Verify performance objective can be created successfully | User should be on the Performance objectives page | Performance → Objectives → Create → Save | https://hris.softwareplus.lk/performance/objectives | Enter valid data | Objective should be created instantly | Objective created successfully | Pass
TC_83 | Performance | Verify performance objective can be updated successfully | User should be on the Performance objectives page | Performance → Dashboard/Objectives → Edit → Save | https://hris.softwareplus.lk/performance/objectives | Enter valid data | Objective should update successfully | Error: Request failed with status code 500 | Fail | Bug_14
TC_84 | Performance | Verify key result can be created successfully | User should be on the Performance key results page | Performance → Key Results → Create → Save | https://hris.softwareplus.lk/performance/key-results | Enter valid data | Key result should be created instantly | Key result created successfully | Pass
TC_85 | Performance | Verify key result can be edited successfully | User should be on the Performance key results page | Performance → Dashboard/Key Results → Edit → Save | https://hris.softwareplus.lk/performance/key-results | Enter valid data | Key result should update successfully | Error: Request failed with status code 500 | Fail | Bug_15
TC_86 | Performance | Verify performance feedback can be created successfully | User should be on the performance 360 Feedback page | Performance → Dashboard/360 Feedback → Create → Save | https://hris.softwareplus.lk/performance/feedback | Enter valid data | Feedback should be created instantly | Feedback created successfully | Pass
TC_87 | Performance | Verify meeting can be scheduled successfully | User should be on the Performance Meetings page | Performance → Meetings → Schedule → Save | https://hris.softwareplus.lk/performance/meetings | Enter valid data | Meeting should be created instantly | Meeting created successfully | Pass
TC_88 | Performance | Verify employee bonus point can be created successfully | User should be on the Employee Bonus Point page | Performance → Bonus Point → Create → Save | https://hris.softwareplus.lk/performance/bonus | Enter valid data | Bonus point should be created instantly | Saved, but not visible in list | Fail | Bug_16
TC_89 | Performance | Verify bonus point list refresh button works correctly | User should be on the Employee Bonus Point page | Performance → Bonus Point → Refresh button | https://hris.softwareplus.lk/performance/bonus | No data required to enter | List should refresh | Button not working | Fail | Bug_17
TC_90 | Performance | Verify performance period can be created successfully | User hsould be on the Performance period page | Performance → Period → Create → Save | https://hris.softwareplus.lk/performance/period | Enter valid data | Period should be created instantly | Error: Failed to create performance period | Fail | Bug_18
TC_91 | Performance | Verify question template can be created successfully | User should be on the Question Template page | Performance → Question Template → Create → Save | https://hris.softwareplus.lk/performance/question-template | Enter valid data | Template should be created instantly | Template created successfully | Pass
TC_92 | Offboarding | Verify exit process can be created successfully | User should be on the Offboarding exit process page | Offboarding → Exit Process → Create → Save | https://hris.softwareplus.lk/exit | Enter valid data | Exit process should be created instantly | Exit process created successfully | Pass
TC_93 | Offboarding | Verify exit process can be updated successfully | User should be on the Offboarding exit process page | Offboarding → Exit Process Management → Click "View" → Edit → Save | https://hris.softwareplus.lk/exit | Enter valid data | Status should update correctly | Status updated correctly | Pass
TC_94 | Offboarding | Verify sidebar remains expanded when navigating offboarding menu | User should open the offboarding dropdown from the sidebar | Offboarding → Sidebar → Click Exit Process | https://hris.softwareplus.lk/offboarding-dashboard | No data required to enter | Sidebar should remain expanded | Sidebar collapses unexpectedly | Fail | Bug_19
TC_95 | Payroll | Verify payroll report can be exported successfully | User should be on the payroll dashboard page | Payroll → Dashboard → Export | https://hris.softwareplus.lk/payroll-dashboard | No data required to enter | Payroll Excel sheet should download | Payroll Excel sheet downloaded correctly | Pass
TC_96 | Payroll | Verify contract can be created successfully | User should be on the payroll Contract page | Payroll → Contracts → Create | https://hris.softwareplus.lk/payroll-contract | No data entered | New contract window should open and save | Logs out, redirects to login page | Fail | Bug_35
TC_97 | Payroll | Verify contract can be edited successfully | User should be on the payroll Contract page | Payroll → Contracts → Edit → Save | https://hris.softwareplus.lk/payroll-contract | Enter valid data | Contract should update and remain logged in | Shows success popup, then logs out; after re-login contract updated | Fail | Bug_36
TC_98 | Payroll | Verify contract can be deleted successfully | User should be on the payroll contract page | Payroll → Contracts → Delete | https://hris.softwareplus.lk/payroll-contract | No data required to enter | Contract should be deleted instantly | Contract deleted successfully | Pass
TC_99 | Payroll | Verify allowance is created with selected color correctly applied | User should be on the Payroll Allowances page | Payroll → Allowances → Create → Save | https://hris.softwareplus.lk/payroll/create-allowance | Enter valid data | Allowance should display with selected color | Allowance created, but color always green | Fail | Bug_37
TC_100 | Payroll | Verify allowance details can be edited successfully | User should be on the Payroll Allowances page | Payroll → Allowances → 3 dots menu → Edit → Save | https://hris.softwareplus.lk/payroll-allowances | Enter valid data | Allowance should update correctly | Allowance updated successfully | Pass
TC_101 | Payroll | Verify allowance can be deleted successfully | User should be on the Payroll Allowances page | Payroll → Allowances → 3 dots menu → Delete | https://hris.softwareplus.lk/payroll-allowances | No data required to enter | Allowance should be deleted instantly | Allowance deleted successfully | Pass
TC_102 | Payroll | Verify all 3-dots menu are clickable | User should be on the Payroll Allowances page | Payroll → Allowances → 3-dots on rightmost card | https://hris.softwareplus.lk/payroll-allowances | No data required to enter | Menu should open | Menu not clickable on rightmost cards | Fail | Bug_38
TC_103 | Payroll | Verify deduction can be created successfully | User should be on the payroll deductions page | Payroll → Deductions → Create → Save | https://hris.softwareplus.lk/payroll-deductions | Enter valid data | Deduction should be created instantly | Deduction created successfully | Pass
TC_104 | Payroll | Verify deductions can be searched without input interruption | User should be on the payroll deductions page | Payroll → Deductions → Search | https://hris.softwareplus.lk/payroll/create-deduction | Enter valid data | Should allow continuous typing | Allows only one letter at a time, reloads | Fail | Bug_39
TC_105 | Payroll | Verify individual payslip can be created successfully | User should be on the Payslips page | Payroll → Payslips → Create Individual → Save | https://hris.softwareplus.lk/payroll-payslips | Enter valid data | Payslip should be created instantly | Error: missing required positional argument 'db' | Fail | Bug_40
TC_106 | Payroll | Verify all payslips can be generated successfully | User should be on the Payslips page | Payroll → Payslips → Actions → Generate All | https://hris.softwareplus.lk/payroll-payslips | No data required to enter | All payslips should generate | Logs out, redirects to login page | Fail | Bug_41
TC_107 | Payroll | Verify payslip can be viewed successfully | User should be on the Payslips page | Payroll → Payslips → Eye icon | https://hris.softwareplus.lk/payroll-payslips | No data required to enter | Payslip should display | Payslip displayed correctly | Pass
TC_108 | Payroll | Verify payslip window UI elements display correctly | User should be on the Payslips page | Payroll → Payslips → Eye icon | https://hris.softwareplus.lk/payroll-payslips | No data required to enter | UI should be formatted correctly | Print/Download button invisible until hover; header incomplete | Fail | Bug_42
TC_109 | Payroll | Verify payslip downloads successfully | User should be on the Payslips page | Payroll → Payslips → Download icon | https://hris.softwareplus.lk/payroll-payslips | No data required to enter | Payslip should download | Opens payslip window instead of downloading | Fail | Bug_43
TC_110 | Payroll | Verify payslip status can be updated successfully | User should be on the Payslips page | Payroll → Payslips → Approve → Paid | https://hris.softwareplus.lk/payroll-payslips | No data required to enter | Status should change correctly | Status changes correctly | Pass
TC_111 | Payroll | Verify loan or advance salary request can be created successfully | User should be on the Loan / Advanced Salary page | Payroll → Loan/Advance Salary → Create → Save | https://hris.softwareplus.lk/payroll-loan | Enter valid data | Loan/Advance salary should be created | Loan/Advance salary created successfully | Pass
TC_112 | Payroll | Verify reimbursement request can be created successfully | User should be on the Encashments & Reimbursements page | Payroll → Encashments & Reimbursements → Create → Select reimbursement → Save | https://hris.softwareplus.lk/payroll-encashments | Enter valid data | Reimbursement should be created instantly | Reimbursement created successfully | Pass
TC_113 | Payroll | Verify leave encashment can be created successfully | User should be on the Encashments & Reimbursements page | Payroll → Encashments & Reimbursements → Create → Select Leave Encashment → Save | https://hris.softwareplus.lk/payroll-encashments | Enter valid data | Leave encashment should be created instantly | Leave encashment created successfully | Pass
TC_114 | Payroll | Verify bonus encashment can be created successfully | User should be on the Encashments & Reimbursements page | Payroll → Encashments & Reimbursements → Create → Select Bonus Encashment → Save | https://hris.softwareplus.lk/payroll-encashments | Enter valid data | Bonus encashment should be created instantly | Bonus encashment created successfully | Pass
TC_115 | Payroll | Verify reimbursement and encashment requests can be approved or rejected successfully | User should be on the Encashments & Reimbursements page | Payroll → Encashments & Reimbursements → Approve/Reject | https://hris.softwareplus.lk/payroll-encashments | No data required to enter | Status should update correctly | Status updated correctly | Pass
TC_116 | Payroll | Verify reimbursements and encashments can be filtered correctly | User should be on the Encashments & Reimbursements page | Payroll → Encashments & Reimbursements → Filter → Apply | https://hris.softwareplus.lk/payroll-encashments | Enter employee name to filter | Should show filtered employee reimbursements | Shows all employees instead | Fail | Bug_44
TC_117 | Payroll | Verify filing status can be created successfully | User should be on the Federal Tax page | Payroll → Federal Tax → Create → Save | https://hris.softwareplus.lk/payroll-federal-tax | Enter valid data | Filing status should be created instantly | Filing status created successfully | Pass
TC_118 | Payroll | Verify payroll request can be created successfully | User should be on the My payroll requests page | Payroll → My Payroll Requests → Create → Submit | https://hris.softwareplus.lk/payroll-requests | Enter valid data | Request should be created instantly | Request created successfully | Pass
TC_119 | Payroll | Verify payroll request status updates correctly after approval or rejection | User should be on the My Payroll requests page | Payroll → My Payroll Requests → Approve/Reject | https://hris.softwareplus.lk/payroll-requests | No data required to enter | Status should update correctly | Status shows “Awaiting admin” under confirmation column | Fail | Bug_45
TC_120 | Assets | Verify User Can Assign an Asset Successfully | User should be on the Assets management page | Assets → Assign New Asset → Save | https://hris.softwareplus.lk/assets | Enter valid data | Asset should be assigned instantly | Asset assigned successfully | Pass
TC_121 | Help Desk | Verify User Can Create a Help Desk Ticket Successfully | User should be on the Help desk page | Help Desk → New Ticket → Submit | https://hris.softwareplus.lk/help-desk | Enter valid data | Ticket should be created instantly | Ticket created successfully | Pass
TC_122 | Help Desk | Verify User Can Edit a Help Desk Ticket Successfully | User should be on the Help desk page | Help Desk → Edit Ticket → Save | https://hris.softwareplus.lk/help-desk | Enter valid data | Ticket should update instantly | Ticket updated successfully | Pass
TC_123 | Project | Verify User Can Create a Project Successfully | User should be on the project management page | Project → New Project → Save | https://hris.softwareplus.lk/project | Enter valid data | Project should be created instantly | Project created successfully | Pass
TC_124 | Project | Verify User Can Delete a Project Successfully | User should be on the project management page | Project → Delete Project → Confirm | https://hris.softwareplus.lk/project | Enter valid data | Project should be deleted instantly | Project deleted successfully | Pass
TC_125 | Configuration | Verify User Can Update Configuration Settings Successfully | User should be on the system configuration page | Configuration → Change settings → Save | https://hris.softwareplus.lk/configuration | Enter valid data | Settings should update instantly | Settings updated successfully | Pass
TC_126 | Global | Verify Application Layout Adapts Correctly Across Different Screen Sizes | HRIS website accessible on multiple devices | Open HRIS website → Resize browser window to smaller screen sizes (tablet/mobile view) | https://hris.softwareplus.lk/login | No data required to enter | Website should adapt layout and remain fully functional | Layout breaks, elements overlap or become unusable; works only in full‑screen desktop view | Fail | Bug_46
TC_127 | Header | Verify View All Notifications Redirects to Notifications Page Successfully | User must be logged in with notifications | Header → Click Notification Bell → Popup opens → Click 'View All Notifications' | https://hris.softwareplus.lk/dashboard | No data required to enter | Should redirect to full notifications page | Nothing happens, no action triggered | Fail | Bug_47

## Bug report
SpaceXP HRIS - Admin Portal
Bug Report
Tested By: V. Deshanth
Application URL |  | https://hris.softwareplus.lk/login
Browser |  | Mozilla Firefox, Microsoft Edge
Operating System |  | Windows 11
Bug ID | Test Case ID | Bug Title | Module | Steps to Reproduce | Link/Environment | Expected Result | Actual Result | Severity | Status | Impact
Bug_01 | TC_01 | Page not loading within 4 seconds | Login page | 1. Open the URL in Edge→ open devtools→ refresh page→Observe the load time 2. Open the URL in firefox→open devtools→refresh page→Observe the load time | https://hris.softwareplus.lk/login | The page should load completely within 4 seconds across both the browsers | Page load time in Edge: less than 2 seconds Page load time in Firefox: More than 4 seconds | Medium | Open | Slower performance in Firefox affects usability
Bug_02 | TC_05 | Forgot password link does not redirect to password reset page | Login page | 1. Visit the URL 2. Click 'Forgot Password?' link | https://hris.softwareplus.lk/login | User should be redirected to the password reset page. | Clicking the link does not redirect the password reset page. No response from the action | High | Open | Users cannot recover forgotten passwords
Bug_03 | TC_06 | Contact HR administrator link is not functioning | Login page | 1. Visit the URL 2. Click 'Contact HR Administrator' link | https://hris.softwareplus.lk/login | User should be redirected to a contact page or HR support page | No response from the link. | Medium | Open | New users cannot create account and reduces usability
Bug_04 | TC_07 | Sidebar does not collapse or expand when toggle button is clicked | Dashboard | 1. Login to the system 2. Click on the sidebar toggle button 3. Observe the change | https://hris.softwareplus.lk/dashboard | The sidebar should open and close when the toggle button is clicked | When the button is clicked the sidebar is not closing, it remains opened | Medium | Open | Takes up more space from the dashboard. UI responsiveness is weak
Bug_05 | TC_08 | Dark overlay appears unexpectedly on admin dashboard | Dashboard | 1. Login to the system 2. Observe the dark effect on the dashboard interface 3. Randomly navigate to other interfaces from the sidebar 4. Observe the same dark effect on other interfaces as well | https://hris.softwareplus.lk/dashboard | User should successfully be logged into the system and redirected to the dashboard without any errors | Dashboard and other interfaces display a dark effect that disappears when randomly clicked in the interface area. | High | Open | Affects admin users, occurs every time. User should click somewhere on the screen to restore to normal view
Bug_06 | TC_19 | Top interviewers card text has does not fit within the card. | Recruitment → Recruitment View | Navigate to Recruitment View → Observe Top Interviewers card | https://hris.softwareplus.lk/recruitment/view | Text should be readable and be within the assigned card | Black text blends with dark navy blue background and long texts exceeds the border of the card | Medium | Open | UI/UX issue, reduces readability
Bug_07 |  | Salary field accepts non-numeric characters when posting a new job | Recruitment → Open Jobs | Navigate to Open Jobs → Post New Job → Enter non-numeric characters in Salary Range → Click Post Job | https://hris.softwareplus.lk/recruitment/open-jobs | Salary field should validate numeric input only | Job posted successfully with invalid salary input | High | Open | Data integrity issue, incorrect salary values possible
Bug_08 | TC_21 | View details button in open jobs page is not responding | Recruitment → Open Jobs | Navigate to Open Jobs → 3-dots menu → Click View Details | https://hris.softwareplus.lk/recruitment/open-jobs | Job details should open | No response from button click | High | Open | Blocks access to job details
Bug_09 | TC_23 | 3-dots menu on rightmost job cards is not clickable | Recruitment → Open Jobs | Resize browser → Try clicking 3-dots on rightmost job card | https://hris.softwareplus.lk/recruitment/open-jobs | Menu should open | Menu not clickable | Medium | Open | Usability issue, inconsistent access to options
Bug_10 | TC_30 | Onboarding pipeline incorrectly marks employee as completed at fourth stage | Recruitment → Onboarding | Add employee to pipeline → Click Mark Ready through stages | https://hris.softwareplus.lk/onboarding | Employee should progress through all stages | At 4th stage, system marks as completed prematurely, pipeline disappears | Critical | Open | Workflow broken, onboarding process incomplete
Bug_11 | TC_68 | Adding biometric device fails with status code 400 error | Attendance → Biometric Devices | Add device → Fill form → Click Add | https://hris.softwareplus.lk/attendance-biometric | Device should be added instantly | Shows “Request failed with status code 400” | High | Open | Blocks adding new devices
Bug_12 | TC_79 | Group by functionality in attendance requests is not working | Attendance → My Attendance Requests | Click Group By | https://hris.softwareplus.lk/attendance-my-requests | Requests should group by category | Button not working | Medium | Open | Reduces usability, poor filtering
Bug_13 | TC_81 | Edit and delete actions in attendance requests behave inconsistently | Attendance → My Attendance Requests | Edit/Delete on approved requests | https://hris.softwareplus.lk/attendance-my-requests | Buttons should be disabled or hidden | Edit dimmed, delete visible but not working | Medium | Open | Confusing UI, poor user experience
Bug_14 | TC_83 | Updating performance objective fails with status code 500 error | Performance → Objectives | Edit objective → Save | https://hris.softwareplus.lk/performance/objectives | Objective should update | Error: Request failed with status code 500 | High | Open | Blocks updating objectives
Bug_15 | TC_85 | Editing key result fails with status code 500 error | Performance → Key Results | Edit key result → Save | https://hris.softwareplus.lk/performance/key-results | Key result should update | Error: Request failed with status code 500 | High | Open | Blocks updating key results
Bug_16 | TC_88 | Created bonus points are not visible in bonus point list | Performance → Bonus Point | Create bonus point → Save | https://hris.softwareplus.lk/performance/bonus | Bonus point should display in list | Saved but list remains empty | High | Open | Data inconsistency, misleading workflow
Bug_17 | TC_89 | Refresh button in bonus point section is not fully clickable | Performance → Bonus Point | Click refresh | https://hris.softwareplus.lk/performance/bonus | List should refresh | Button not clickable on the entire button area | Medium | Open | Usability issue
Bug_18 | TC_90 | Performance period creation fails with error message | Performance → Period | Create period → Save | https://hris.softwareplus.lk/performance/period | Period should be created | Error: Failed to create performance period | High | Open | Blocks performance cycle setup
Bug_19 | TC_94 | Sidebar collapses unexpectedly during exit process navigation | Offboarding → Sidebar | Click Exit Process | https://hris.softwareplus.lk/offboarding-dashboard | Sidebar should remain expanded | Sidebar collapses | Medium | Open | UI inconsistency, poor navigation
Bug_20 | TC_32 | Internal server error displayed while adding employee despite successful creation | Employee → Employees | Add employee → Fill form → Click Add | https://hris.softwareplus.lk/employee-employees | Employee should be added instantly | Shows “Internal server error”, employee appears only after refresh | High | Open | Misleading error message, workflow disruption
Bug_21 | TC_33 | Document request creation shows failure message until page refresh | Employee → Document Request | Create request → Fill form → Save | https://hris.softwareplus.lk/employee-document-requests | Request should appear instantly | Shows “Failed to create document request”, appears only after refresh | High | Open | Misleading error message, delayed visibility
Bug_22 | TC_39 | Rotating shift assignment displays failure message until page refresh | Employee → Rotating Shift Assign | Assign shift → Fill form → Click Assign | https://hris.softwareplus.lk/employee-rotating-shift-assign | Assignment should appear instantly | Shows “Failed to assign rotating shift”, appears only after refresh | High | Open | Misleading error message, delayed visibility
Bug_23 | TC_41 | Rotating work type assignment displays failure message until page refresh | Employee → Rotating Work Type Assign | Assign work type → Fill form → Click Assign | https://hris.softwareplus.lk/employee-rotating-work-type-assign | Assignment should appear instantly | Shows “Failed to assign work type”, appears only after refresh | High | Open | Misleading error message, delayed visibility
Bug_24 | TC_44 | Downloading disciplinary attachment logs user out of the system | Employee → Disciplinary Actions | Create action with attachment → Click Download | https://hris.softwareplus.lk/employee-disciplinary-actions | Attachment should download | Logs user out, redirects to login page | Critical | Open | Security flaw, breaks workflow
Bug_25 | TC_50 | Edit and delete actions work only for pending requests without proper indication | Employee → My Other Requests | Click Edit/Delete on non-pending requests | https://hris.softwareplus.lk/employee-other-requests | Buttons should be disabled or hidden | Buttons visible but non-functional | Medium | Open | Confusing UI, poor user experience
Bug_26 | TC_52 | Personal leave dashboard does not open when clicked | Leave → Dashboard | Click Personal Dashboard card | https://hris.softwareplus.lk/leave-dashboard | Dashboard should open | No response | Medium | Open | Blocks access to personal dashboard
Bug_27 | TC_54 | Leave request creation fails due to missing leave allocation | Leave → My Leave Requests | Create request → Save | https://hris.softwareplus.lk/leave-my-requests | Request should be created | Error: “No leave allocation found” | High | Open | Prevents admins from creating leave requests
Bug_28 | TC_55 | Leave request page goes blank after clicking save | Leave → Leave Request | Create request → Save | https://hris.softwareplus.lk/leave-requests | Request should be created | Page goes blank | Critical | Open | Workflow broken, system unusable
Bug_29 | TC_56 | Leave request deletion fails with error message | Leave → Leave Request | Delete request | https://hris.softwareplus.lk/leave-requests | Request should be deleted | Error: “Failed to delete” | High | Open | Prevents removal of leave requests
Bug_30 | TC_58 | Assigned leave is not visible after successful assignment message | Leave → Leave Types | Assign leave to employees | https://hris.softwareplus.lk/leave-types | Leave should be visible in assigned leave page | Success message shown, but not reflected | High | Open | Misleading success message, data inconsistency
Bug_31 | TC_59 | Edit button in leave types page is not responding | Leave → Leave Types | Click Edit | https://hris.softwareplus.lk/leave-types | Leave type should be editable | No response | Medium | Open | Prevents editing leave types
Bug_32 | TC_61 | 3-dots menu on the rightmost leave type cards is not clickable | Leave → Leave Types | Click 3-dots on rightmost card | https://hris.softwareplus.lk/leave-types | Menu should open | Menu not clickable | Medium | Open | Usability issue, inconsistent access
Bug_33 | TC_62 | Assigned leave creation fails with error message | Leave → Assigned Leave | Assign leave → Save | https://hris.softwareplus.lk/leave-assigned | Leave should be assigned | Error: “Failed to assign leaves” | High | Open | Prevents assigning leaves
Bug_34 | TC_63 | Edit button in assigned leave page is not responding | Leave → Assigned Leave | Click Edit | https://hris.softwareplus.lk/leave-assigned | Leave should be editable | No response | Medium | Open | Prevents editing assigned leaves
Bug_35 | TC_96 | Creating payroll contract logs user out of the system | Payroll → Contracts | Create contract → Save | https://hris.softwareplus.lk/payroll-contract | Contract should be created | Logs out, redirects to login page | Critical | Open | Blocks contract creation
Bug_36 | TC_97 | Editing payroll contract logs user out after successful update | Payroll → Contracts | Edit contract → Save | https://hris.softwareplus.lk/payroll-contract | Contract should update | Shows success popup, then logs out | Critical | Open | Workflow disruption, but data saved
Bug_37 | TC_99 | Allowance color selection is ignored and defaults to green | Payroll → Allowances | Create allowance → Select color | https://hris.softwareplus.lk/payroll-allowances | Selected color should display | Always green | Medium | Open | UI inconsistency
Bug_38 | TC_102 | 3-dots menu on rightmost allowance cards is not clickable | Payroll → Allowances | Click 3-dots on rightmost card | https://hris.softwareplus.lk/payroll-allowances | Menu should open | Menu not clickable | Medium | Open | Usability issue
Bug_39 | TC_104 | Deduction search field allows only one character input at a time | Payroll → Deductions | Type in search bar | https://hris.softwareplus.lk/payroll-deductions | Continuous typing should work | Reloads after each letter | Medium | Open | Poor usability
Bug_40 | TC_105 | Individual payslip creation fails due to missing database argument | Payroll → Payslips | Create individual payslip | https://hris.softwareplus.lk/payroll-payslips | Payslip should be created | Error: missing argument 'db' | Critical | Open | Blocks payslip creation
Bug_41 | TC_106 | Generating all payslips logs user out of the system | Payroll → Payslips | Click Generate All | https://hris.softwareplus.lk/payroll-payslips | All payslips should generate | Logs out, redirects to login page | Critical | Open | Blocks bulk generation
Bug_42 | TC_108 | Payslip window UI elements are improperly displayed | Payroll → Payslips | View payslip window | https://hris.softwareplus.lk/payroll-payslips | UI should be formatted correctly | Print/Download button invisible, header incomplete | Medium | Open | Poor UI/UX
Bug_43 | TC_109 | Download payslip button opens payslip window instead of downloading file | Payroll → Payslips | Click Download icon | https://hris.softwareplus.lk/payroll-payslips | Payslip should download | Opens view window instead | High | Open | Misleading functionality
Bug_44 | TC_116 | Reimbursement and encashment filters display incorrect employee data | Payroll → Encashments & Reimbursements | Apply filter for employee | https://hris.softwareplus.lk/payroll-encashments | Should show filtered employee reimbursements | Shows all employees | Medium | Open | Data filtering issue
Bug_45 | TC-119 | Payroll request confirmation status does not update correctly | Payroll → My Payroll Requests | Approve/Reject request | https://hris.softwareplus.lk/payroll-requests | Status should update correctly | Shows “Awaiting admin” | High | Open | Misleading status, workflow confusion
Bug_46 | TC_126 | Application layout breaks on smaller screen sizes | Global (Header, Dashboard, All modules) | 1. Open HRIS website 2. Resize browser window to smaller screen sizes (tablet/mobile) | https://hris.softwareplus.lk/login | Website should adjust layout and remain usable | Layout breaks, elements overlap, navigation unusable; works only in full-screen desktop | High | Open | Blocks usability on mobile/tablet devices, poor accessibility
Bug_47 | TC_127 | View all notifications button does not redirect to notifications page | Header → Notifications | 1. Click Notification Bell 2. Popup opens 3. Click 'View All Notifications' | https://hris.softwareplus.lk/dashboard | Should redirect to full notifications page | Nothing happens, no action triggered | Medium | Open | Users cannot access full notification history, workflow disruption
Bug_48 | TC_69 | Employee selection window lacks confirmation button to add attendance | Attendances | 1. Open Attendances page under the Attendance section from the sidebar 2. Click "Add attendance" 3. Click the employee dropdown to select the employee 4. Observe theres a missing confirmation button | https://hris.softwareplus.lk/attendance-attendances | Should be able to confirm the selected employees from the dropdown | There is no button to confirm the selected employees to add to the list. The selected employees are added to the list only when clicked oustide the poped open window | Medium | Open | Poor usability
Bug_49 | TC_72 | Sidebar indicator shifts to Dashboard after Create action | Attendance→ Hour Account | 1. Open Hour Account under Attendance from the sidebar 2. Click "Create" 3.Click "Go to attendance" 4. Observe the Sidebar indicator change | https://hris.softwareplus.lk/attendance-attendances | The sidebar indicator should remain in the same | Once the action is complete, the page reloads and lands correclty but the sidebar indicator changes. | Medium | Open | Poor usability